## Product backlog
Weather on Mobile
ID | Description | Sprint # | 1 | 2 | 3 | 4 | 5 | 6
|  | Effort needed for Release 1 as in the beginning of the sprint | 90 | 70 | 34 | 0 | 0 | 0
1 | Set up continuous integration system |  | 5 | 0 | 0 | 0 | 0 | 0
2 | Create compilable application skeleton |  | 5 | 0 | 0 | 0 | 0 | 0
3 | Display current temperature in a simplest possible way |  | 13 | 0 | 0 | 0 | 0 | 0
4 | Set up the web server for serving weather data |  | 3 | 0 | 0 | 0 | 0 | 0
5 | Implement stubby WeatherML support on the server side |  | 13 | 0 | 0 | 0 | 0 | 0
Sprint 1 | Make sample data go from server to device
6 | Graphics support on the client side |  | 20 | 0 | 0 | 0 | 0 | 0
16 | Make the graphics library draw some icon and sample temperature text |  | - | 13 | 0 | 0 | 0 | 0
17 | Draw the real weather screen |  | - | 8 | 0 | 0 | 0 | 0
7 | Implement support for several days |  | 8 | 8 | 0 | 0 | 0 | 0
8 | Implement support for rain, snow, etc. icons |  | 2 | 2 | 0 | 0 | 0 | 0
9 | City changing support |  | - | 5 | 0 | 0 | 0 | 0
Sprint 2 | Minimal working version
10 | Fetch one day temperature data from the weather provider system |  | ? | 13 | 13 | 0 | 0 | 0
11 | Fetch rain, snow, etc details from the provider |  | 8 | 8 | 8 | 0 | 0 | 0
12 | Fetch several days data from the provider |  | 5 | 5 | 5 | 0 | 0 | 0
13 | Auto-refresh feature |  | 8 | 8 | 8 | 0 | 0 | 0
Sprint 3 | Plug in the real weather data
Release 1 | Sellable version
14 | Inject simulated ads from the test server |  | 20 | 20 | 20 | 20 | 20 | 20
15 | Plug real ads in |  | 20 | 20 | 20 | 20 | 20 | 20
18 | Change current city automatically according to the cell info |  | 40 | 40 | 40 | 40 | 40 | 40
Sprint 4 | Advertisements support
Release 2 | Ad-supported version
| Effort in the whole backlog |  | 170 | 150 | 114 | 80 | 80 | 80
Backlog state taken after the end of sprint 3 = after release 1
http://agilesoftwaredevelopment.com/simple-product-backlog
Note on A34: See for reference and comments. Feel free to remove the link. Though it would be very kind of you to leave it present somewhere on the sheet
Note on B19: In a real product backlog, items are more likely to be in the form of user stories. E.g. this item could be stated as "As a user I want to see the real weather data so that I could know what to wear before leaving home"
Note on D11: It is important to see how much effort was done during each sprint (team velocity). However, it would complicate the simplest formulae used here. So, for the simplest backlog it might be easier to calculate velocity manually.
Note on D13: This product backlog item was added to the product backlog after the first sprint. Therefore no estimation during sprint 1
Note on D19: Team was so uncertain about this item during sprint one, that the estimated size was a complete question mark. Some experiments were carried out during sprint one in order to get a handle on the size
Note on E5: Effort as in the beginning of sprint 2
Note on E20: Note formulae. It is convenient to have values copied automatically until there is a reason to change the estimation